ERASMUS+ PROGRAMME

Project Number: 610134-EPP-1-2019-1-JO-EPPKA2-CBHE-JP

HEALING:

Developing a Multidisciplinary Diploma on Art Therapy in Health Education

Minutes of

the Online Kick-off Meeting

The University of Jordan

Amman-Jordan

March 19, 2020

ERASMUS+ PROGRAMME

Project Number: 610134-EPP-1-2019-1-JO-EPPKA2-CBHE-JP

HEALING:

Developing a Multidisciplinary Diploma on Art Therapy in Health Education

Minutes of

the Online Kick-off Meeting

The University of Jordan

Amman-Jordan

March 19, 2020

Participant List

| No. | Participant Name | Position |
| --- | --- | --- |
| The University of Jordan |  |  |
|  | Prof. Ahmed Al-Salaymeh | Project Coordinator and Professor at the School of Engineering. |
|  | Prof. Rami Haddad | Dean of School of Arts |
|  | Prof. Islam Massad | Dean of the School of Medicine |
|  | Prof. Mohammad AlShraideh | Dean of the School of Graduate Studies |
|  | Eng. Leena Marashdeh | Research Assistant |
|  | Ms. Hanan Hasan | Research Assistant |
|  | Eng. Rasha Al-Beek | Research Assistant |
|  | Eng. Tahani Adi | Research Assistant |
|  | Eng. Narees Melhem | Research Assistant |
| The Hashemite University |  |  |
|  | Prof. Darwish Badran | Dean of the School of Medicine |
|  | Dr. Aiman Al Sharei | Associate professor at the School of Medicine |
|  | Dr. Mamoon Obeidat | Assistant professor at Prince Al-Hussein bin Abdullah II Faculty of Information Technology |
| Irbid National University |  |  |
|  | Prof. Ahmad Khasawneh | President of Irbid National University |
|  | Prof. Ahmad Odat | President Assistant of Irbid National University and Professor at School of Information technology |
|  | Dr. Roqia Maabreh | Assistant professor at Nursing Faculty |
|  | Dr. Riyad Al-Dgheim | Assistant professor at Nursing Faculty |
| Jordan University of Science and Technology |  |  |
|  | Eng. Ruba Hasan | Research Assistant |
| Israa University |  |  |
|  | Dr. Ghaida Abu Rumman | President Assistant and Director of Training continuous Education and Community Service Centre |
| University of Gabes |  |  |
|  | Dr. Mehdi Khouja | Assistant Professor at Higher Institute of Computer and Multimedia |
|  | Dr. Mohamed Ouwais Kabaou | Associate professor in Computer Science , Head of E-Learning Department |
|  | Dr. Hela Hassine | Assistant Professor in Science and Techniques of Art at Higher Institute of Computer Sciences and multimedia |
| University of Sfax |  |  |
|  | Dr. Ismail Bouassida | Associate professor in Computer Science |
|  | Dr. Slim Kallel | Associate professor in Computer Science |
|  | Dr. Amine Elleuch | Associate professor in Department of Biology |
| University of Sousse |  |  |
|  | Dr. Adel Boullegue | Associate Professor at the National Engineering School |
|  | Dr. Wassim Jomaa | Associate Professor at Higher Institute of Musicology |
| University of Brescia |  |  |
|  | Dr. Giovanni Mirabella | Associate Professor of physiology |
| Porto Polytechnic |  |  |
|  | Dr. Carlos Vaz de Carvalho | Associate Professor of the Computer Engineering Department |
| National and Kapodistrian University of Athens |  |  |
|  | Dr. Sofia Papakonstantinou | Team Member |
| Universidade Católica Portuguesa |  |  |
|  | Dr. Mariana Reis Barbbosa | Assistant Professor of Psychology |
| University of Osijek |  |  |
|  | Prof. Berislav Jerkovic | Head of Music department |
|  | Prof. Antoaneta Radocaj | Professor at Osijek Art Academy |
|  | Dr. Antonija Matic | Head of the Office for EU Projects and Programs |
| University College Limburg vzw |  |  |
|  | Ms. Chloe Mentens | Project Researcher |
|  | Ms. Nele Keltchtermans | Project Researcher |

# Minutes of the Meeting

The meeting was conducted via zoom video conferencing due to the global crisis, Corona Virus.

The meeting started by a welcome from the Project Coordinator, Prof. Ahmed Al-Salaymeh. Then the participants introduced themselves (Name and Institution).

## HEALING Project in Brief

Prof. Ahmed Al-Salaymeh presented HEALING Project in Brief. He outlined the project objectives, indicators, expected results of work packages and their overall plan. The overall plans will be as follow:

### WP1:  In-depth analyses of the overall situation on the on Art Therapy in Education

Duration: M2 to M7

Lead University: University College Limburg VZW

Co-Lead University: Irbid National University & University of Sousse

Overall Plan:

- WP leader will set a detailed plan for the WP with due dates by M1

- WP leader will design the four surveys in coordination with WP2 leader and submit them to be approved by Technical Committee by M2

- Partners will circulate the surveys to the target groups

- Co-leaders will analyse the responses under the leader supervision and generate two reports (one for Jordan and one for Tunisia) by M7

- Other WP’s will be based on generated results of this surveys.

- Progress report to be provided by WP leader every 6 months based on collected feedback from Co-Leaders

### WP 2: Curricula Development

Duration: M7 to M36

Lead University: University of Brescia

Co-Lead University: Al-Isra'a University & University of Gabes

Overall Plan:

- WP leader will set a detailed plan for the WP with due dates by M5-M7

- Courses selection by M8 based on WP1 results

- WP leader will prepare a course outline template with learning outcomes by M9

- Creation of committees responsible to develop the selected courses by M10

- Courses are developed by M15

- Diploma accreditation by M18

- 3-day National Workshop on Curricula Updating by M22

- Piloting phase M24-M36

- Progress report to be provided by WP leader every 6 months based on collected feedback from Co-Leaders

### WP 3: Capacity Building and Training Workshops

Duration: M12 to M36

Lead University: Universidade Católica Portuguesa UCP

Co-Lead University: Hashemite University & University of Sfax

Overall Plan:

- WP leader will set a detailed plan for the WP with due dates by M7

- WP leader will set selection criteria for the workshops by M7

- Workshop topics will be matching the hosting university expertise (Topics in Arts therapy and how to prepare and teach e-courses), the workshop will be as follow:

- (5) Training workshops in 5 EU countries for (32) Teaching staff & (16) technicians

- (1 or 2) Training workshop for in 1 or 2 EU countries (16) students in Europe

- (8) Technology-enhanced (In-house) teacher training (600) staff trained

- Progress report to be provided by WP leader every 6 months based on collected feedback from Co-Leaders

### WP 4: Development of the Art Therapy Centre

Duration: M7 to M18

Lead University: Porto Polytechnic

Co-Lead University: University of Sousse & The University of Jordan

Overall Plan:

- WP leader will set a detailed plan for the WP with due dates by M7

- Prepare a list of main components in Art therapy centers by M9

- WP leader and co-leaders will set the list of needed equipment based on WP1 by M10

- Central Tender is published by M10

- Center is fully equipped and operational by M18

- Progress report to be provided by WP leader every 6 months based on collected feedback from Co-Leaders

### WP5: Quality Control and Monitoring

Duration: M2 to M36

Lead University: National and Kapodistrian University of Athens

Co-Lead University: Jordan University of Science and Technology & University of Gabes

Overall Plan:

- Quality committee will be formed after the kick off meeting by sending emails indicating the nominated members

- WP leader will prepare a summary table that include all activities, deliverables of the project and their method of evaluation with their quality indicators by M3

- WP leader will set a Quality and Monitoring Plan for the WP with due dates annexed with the Quality assurance tools (i.e. evaluation forms, checklists, etc.) by M6

- WP leader will prepare online evaluation links for all meetings, workshops and circulate them to partners after each event, and the results will be analyzed by the WP leader and the co-leaders

- WP leader will prepare online evaluation links for all piloted courses, and circulate them to partners, and the results will be analyzed by the WP leader

- Courses will be peer reviewed against a developed checklist, courses committee will revise the prepared material accordingly.

- External evaluator will be appointed by WP leader by M10

- 3 Quality committee meetings will be conducted in Brescia, Brussels, Sousse

- Progress report to be provided by WP leader every 6 months based on collected feedback from Co-Leaders

### WP6: Dissemination & Exploitation

Duration: M1 to M36

Lead University: Josip Juraj Strossmayer University of Osijek

Co-Lead University: Irbid National University & University of Sfax

Overall Plan:

- Dissemination committee will be formed after the kick off meeting by sending emails indicating the nominated members

- WP leader will set a detailed plan for the WP with due dates by M3, it will include plans for Dissemination, Sustainability and Networking

- Project website will be designed, hosted and managed by University of Jordan by M2

- Facebook page will be created and managed by University of Jordan by M2

- E-Learning platform will be created and managed by University of Jordan by M12

- Promotional Materials will be designed by Work Package leader by M2

- Two national dissemination workshops and will be organized in Jordan and Tunisia

- A three-day Final dissemination conference will be held at University of Jordan by M36

- Creating a Network of Arts Therapists, Community Support professionals, and other stakeholders. The Network members will be involved in different activities of the project.

- Progress report to be provided by WP leader every 6 months based on collected feedback from Co-Leaders, the report will cover all Work packages.

### WP7: Project Coordination

Duration: M1 to M36

Lead University: University of Jordan

Co-Lead University: All

Overall Plan:

- A Steering Committee (SC) will be established with 1 representative and 1 substitute from each partner after the kick off meeting by sending emails indicating the nominated members

- A Technical and Scientific Committee (TSC) will be established with 1 representative and 1 substitute from each partner will be formed after the kick off meeting by sending emails indicating the nominated members

- 6 coordination meetings will be conducted in Amman, Athens, Brescia, Brussels, Porto, and Sousse

- Monthly virtual status meetings via web-conferencing will be held

- Regular communication will be conducted by e-mail and shared electronic database

- Progress report will be prepared every six months

## Session (1): Introduction about Partners

Each partner has delivered a short presentation about their Organization, Staff, Related expertise to Art Therapy, Available programs in Art Therapy, according to the following sequence:

- P1: The University of Jordan, by Prof. Rami Hadad

- P2:  The Hashemite University, by Prof. Aiman Al-Sharei

- P3: Irbid National University, by Prof. Ahmad Odat

- P4: Jordan University of Science and Technology, by Eng. Ruba Hasan

- P5:  Israa University, by Dr. Ghaida Aburumman

- P6: Université de Gabès, by Dr. Mehdi Khouja

- P7: University of Sfax, by Dr. Ismail Bouassida

- P8: University of Sousse, by Dr. Adel Bouallegue

- P9: University of Brescia, by Dr. Giovanni Mirabella

- P10: Porto Polytechnic, by Prof. Carlos Vaz de Carvalho

- P11: National and Kapodistrian University of Athens, by Prof. Thomas Babalis and Dr. Sofia Papakonstantinou

- P12: Universidade Católica Portuguesa, by Prof. Luís Teixeira (Absent)

- P13: University of Osijek, Croatia, by M.Sc. Antonija Matić

- P14: University College Limburg vzw, UCLL, by Ms. Chloe Mentens

### Conclusions of Session 1:

The EU partners have an excellent expertise and facilities that servers the project:

P9-University of Brescia: It has a number of facilities that are extremely useful for the project aim:

- School of Psychodrama

- Medical devices that could record (e.g., fMRI, EEG) as well as interfere (TMS, tDCS) with brain activity. They are also equipped with several psychophysical setups, and thus it can record behavioural responses (EMG, eye movements, vegetative signals) of participants while they are performing cognitive tasks.

- There are research programs aimed to find complementary therapeutic interventions for neurological disease (e.g., we measure the changes in gait parameters of Parkinson’s patients before and after the experience of Santiago Compostela walk).

P10-Porto Polytechnic: IPP has a specialized SCHOOL OF MUSIC AND PERFORMING ARTS that boasts a highly reputable art education and a partnership network at local, national and international levels. ESMAE has an international standing, and offer customised and cutting-edge higher education programmes in music and drama.

P12- Universidade Católica Portuguesa: The Digital Creativity Center (CCD) at UCP, acknowledged as one of the anchor projects from the Creative Industry Cluster in Northern Portugal, is a center of competence and creative excellence with an infrastructure equipped with cutting edge technology in the areas of Digital and Interactive Arts, Computer Music, Sound Design, Audiovisual and Cinematic Arts, Computer Animation.

P13- University of Osijek: The Academy of Arts and Culture the Academy in Osijek is well-known for the organization of numerous conferences, festivals, seminars, book presentations, concerts, exhibitions, plays, projections, music events and workshops. It offers 4 Postgraduate specialist study programme CREATIVE THERAPIES:

- Music therapy

- Dance movement therapy

- Art therapy

- Drama therapy

P14- University College Limburg vzw, UCLL

UCLL hosts eight research centres: Art of Teaching, Education & Development, Health Innovation, Inclusive Society, Resilient People, Smart Organisations, Digital Solutions, & Sustainable Resources. UC Leuven-Limburg is and has been involved in a variety of European projects: under Erasmus+ under, H2020, and other EC programmes (ERDF, REC, AMIF, Interreg, …).

## Session (2): The Set Plans for Implementing all WP’s

Each WP leader has presented the preliminary plan of the work package and discussed it with all partners.

### WP1: In-depth analyses of the overall situation on the on Art Therapy in Education

| Major Activities | Leader | Co- Leader | Other partners involved | Estimated Start\End Date |  |
| --- | --- | --- | --- | --- | --- |
| Task 1.1: In-depth Survey on State of art of Art Therapy in Education | UCLL | INU US | All Partners | M1 | M5 |
| Task 1.2: In-depth Survey on Teachers and Students Competences and awareness |  |  |  | M1 | M5 |
| Task 1.3: In-depth Survey on available facilities and resources |  |  |  | M1 | M5 |
| Task 1.4: Analysis of surveys’ results and elaboration of final Reports |  |  |  | M5 | M6-M7 |

Dr. Chloe Mentens (UCLL) presented the tasks and activities of this work package and the action plan for preparing needed surveys. The partners agreed on the following:

| No. | Task | Responsibility | Due Date |
| --- | --- | --- | --- |
|  | Set a detailed plan | UCLL | M2 |
|  | Prepare the first drafts of the three surveys | UCLL | M2 |
|  | Review the surveys by the quality committee and send comments | Quality Committee | M3 |
|  | The responses will be collected | JO partners TU partners | M3-M5 |
|  | The surveys will be analyzed, and the final report including the three surveys analysis will be prepared | UCLL INU US | M6-M7 |
|  | Progress report to be provided by WP leader every 6 months based on collected feedback from Co-Leaders | UCLL INU US | M6, M12 |

### WP2: Curricula Development

| Major Activities | Leader | Co- Leader | Other partners involved | Estimated Start\End Date |  |
| --- | --- | --- | --- | --- | --- |
| Task2.1: Definitions and Selection of Courses to be updated. | UNIBS | IU UNIVGB | All Partners | M7 | M8 |
| Task2.2: Design of new courses and restructuring of existing courses. |  |  |  | M8 | M15 |
| Tas2.3: National Workshop on Curricula Development |  |  |  | M15 | M19 |
| Task2.4: Implementation & Accreditation of the courses into Curricula. |  |  |  | M20 | M36 |

Dr. Giovanni Mirabella (UNIBS) presented the tasks and activities of Curricula Development work package and the action plan for the accreditation system. The following were concluded:

| No. | Task | Responsibility | Due Date |
| --- | --- | --- | --- |
|  | The diploma will be interdisciplinary, that requires coordination between different faculties | JO Partners TU partners | During Project |
|  | The list of suggested courses will be prepared based on WP1 results | UNIBS IU UNIVGB | M8 |
|  | WP leader will prepare a course outline template with learning outcomes and ECTS component according to Bologna requirements | UNIBS | M9 |
|  | Creation of committees responsible to develop the selected courses | UNIBS IU UNIVGB | M10 |
|  | Courses are fully developed as e-courses | Courses Committees | M15 |
|  | New Programme is fully accredited (Diploma/Master) | JO Partners TU partners | M18 |
|  | 3-day National Workshop on Curricula Updating will be conducted in Tunisia and Jordan | JO Partners TU partners | M15-M19 |
|  | Piloting phase | JO Partners TU partners | M20-M36 |
|  | Progress report to be provided by WP leader every 6 months based on collected feedback from Co-Leaders | UNIBS IU UNIVGB | M12, M18, M24, M30, M36 |

### Presentations about Accreditation procedures in partner universities

Each partner from Jordan and Tunisia presented the accreditation procedure for new programmes in their institutions, the specific target groups and the requirements to enrol in the diploma and the plans to include some courses into existing programmes courses.

The new programme in Art therapy requires coordination from different disciplines such as Art, Educational Psychology, Counseling and Special Education, Psychiatric Mental Health Nursing, and Medicine.

It was concluded that the accreditation takes a long time in some universities (about one year) and include internal and external levels, which urges to start the accreditation process once the courses have been defined.

Also; it was concluded that the Art Therapy program requires a certain level of personal maturity and self-awareness appropriate for the therapeutic activity. Applicants must have an adequate degree of psychological maturity including the ability to achieve and maintain an adequate and empathetic client relationship; they must also show emotional stability and self-reflectiveness.

Accordingly, the target groups, may be many student holding a license / master’s in music and Musicology, Humanities or Social Sciences, (Psychology, Psychomotricity, Ergotherapy or any similar field specified by the steering committee).

### WP3: Capacity Building and Training Workshops (Teacher/Technician Staff & Students)

| Major Activities | Leader | Co- Leader | Other partners involved | Estimated Start\End Date |  |
| --- | --- | --- | --- | --- | --- |
| Task 3.1: Elaboration of Capacity Building Plan & Selection Criteria | UCP | HU USFAX | All Partners | M1 | M7 |
| Task 3.2: Academic and Technician Visits to EU Partners |  |  |  | M7 | M20 |
| Task 3.3: Students Visits to EU Partners |  |  |  | M24 | M30 |
| Task 3.4: Academic workshops for transferring know-how and skills |  |  |  | M20 | M36 |

Prof. Ahmed Al- Salaymeh (UJ), presented the tasks and activities of this work package and the action plan for the implementation since the work package leader contact person was not connected. The partners agreed on the following:

| No. | Task | Responsibility | Due Date |
| --- | --- | --- | --- |
|  | Preparing the capacity building plan including the aims, the training time table and destinations, the suggested agenda, and the selection criteria for staff and students communicate with European partner. Workshop topics will be matching the hosting university expertise (Topics in Arts therapy and how to prepare and teach e-courses) | UCP | M7 |
|  | (5) Training workshops in 5 EU countries for (32) Teaching staff & (16) technicians | EU Partners | M7-M20 |
|  | (1 or 2) Training workshop for in 1 or 2 EU countries (16) students in Europe | EU Partners | M24-M30 |
|  | (8) Technology-enhanced (In-house) teacher training (600) staff trained | JO Partners TU partners | M20-M36 |
|  | Each workshop will be documented through a well prepared report includes (List of participants, agenda, description of activities, link of training material, results of evaluation surveys, and photos) | Hosting University | After workshop |
|  | Progress report to be provided by WP leader every 6 months based on collected feedback from Co-Leaders | UCP HU USFAX | M12, M18, M24, M30, M36 |

### WP4: Development of the Art Therapy Centre to support the new curriculum

| Major Activities | Leader | Co- Leader | Other partners involved | Estimated Start\End Date |  |
| --- | --- | --- | --- | --- | --- |
| Task 4.1: Final List of Equipment | IPP | UJ US | All Partners | M7 | M9 |
| Task 4.2: Purchase, installation of equipment and Lab operation. |  |  |  | M10 | M18 |

Also, Prof, Ahmed Al-Salaymeh (UJ) presented a brief about WP4 with discussing equipment purchasing process with Jordanian and Tunisian Partners, since the work package leader contact person was not connected. The partners agreed on the following:

| No. | Task | Responsibility | Due Date |
| --- | --- | --- | --- |
|  | WP leader will set a detailed plan for the WP | IPP | M7 |
|  | Prepare a list of main components in Art therapy centers according to EU standards | IPP | M7 |
|  | WP leader and co-leaders will set a the list of needed equipment based on WP1 | IPP UJ US | M9 |
|  | Central Tender is announced by University of Jordan for Jordanian Partners | UJ | M10 |
|  | Tunisian Universities will announce the tender call | TU partners | M10 |
|  | Tender should include the tax exemption term, as Equipment is exempted from taxes, and the tax could not be charged to the project | JO Partners TU partners | M10 |
|  | Center is fully equipped and operational | JO Partners TU partners | M18 |
|  | Progress report to be provided by WP leader every 6 months based on collected feedback from Co-Leaders | IPP UJ US | M12, M18, M24, M30, M36 |

### WP5: Quality Control and Monitoring (QC&M)

| Major Activities | Leader | Co- Leader | Other partners involved | Estimated Start\End Date |  |
| --- | --- | --- | --- | --- | --- |
| Task 5.1: Quality Committee | NKUA | JUST UNIVGB | All Partners | M1 | M2 |
| Task 5.2: Quality and Monitoring Plan |  |  |  | M1 | M6 |
| Task 5.3: Quality and Monitoring Reports |  |  |  | M3 | M36 |
| Task 5.4: External Evaluation |  |  |  | M10 | M36 |

Dr. Sofia Papakonstantinou (NKUA) presented WP5 and discussed with all partners the planning for Quality control and monitoring process and all partners agreed on the following:

| No. | Task | Responsibility | Due Date |
| --- | --- | --- | --- |
|  | Quality committee will be formed during the kick off meeting. - 6 persons from Europe (P11: NKUA, P9: UNIBS, P10: IPP, P12: UCP, P13: UNIOS, P14: UCLL), - 1 person from P1: UJ, - 1 person from P4: JUST and - 1 from P6: UNIVGB. | NKUA | M1-M2 |
|  | WP leader will prepare a summary table that include all activities, deliverables of the project and their method of evaluation with their quality indicators | NKUA | M3 |
|  | WP leader will set a Quality and Monitoring Plan for the WP with due dates annexed with the quality assurance tools (i.e. evaluation forms, checklists, etc.) | NKUA | M6 |
|  | WP leader will prepare online evaluation links for all meetings, workshops and circulate them to partners after each event, and the results will be analyzed by the WP leader and the co-leaders | NKUA JUST UNIVGB | Over Project life |
|  | Courses will be peer reviewed against a developed checklist, courses committee will revise the prepared material accordingly. | Quality Committee and Scientific Committee | M15 |
|  | WP leader will prepare online evaluation links for all piloted courses, and circulate them to partners, and the results will be analyzed by the WP leader | NKUA JUST UNIVGB | M20-M36 |
|  | 3 Quality committee meetings will be conducted in Brescia, Brussels, Sousse | NKUA JUST UNIVGB | With the 3 steering committee meetings |
|  | External evaluator will be appointed by WP leader | NKUA | M10 |
|  | Progress report to be provided by WP leader every 6 months based on collected feedback from Co-Leaders | NKUA JUST UNIVGB | M6, M12, M18, M24, M30, M36 |

### WP 6: Dissemination & Exploitation

| Major Activities | Leader | Co- Leader | Other partners involved | Estimated Start\End Date |  |
| --- | --- | --- | --- | --- | --- |
| Task 6.1: Dissemination Committee and Dissemination plan | UNIOS | INU USFAX | All Partners | M1 | M3 |
| Task 6.2: Project Website |  |  |  | M1 | M2 |
| Task 6.3: Dissemination Material |  |  |  | M1 | M2 |
| Task 6.4: E-Learning platform |  |  |  | M11 | M12 |
| Task 6.5: Final Conference |  |  |  | - | M36 |

Dr. Antonija Matic (UNIOS), presented the tasks and activities of this work package and the action plan HEALING Project Dissemination and Exploitation. The partners agreed on the following:

| No. | Task | Responsibility | Due Date |
| --- | --- | --- | --- |
|  | Dissemination committee will be formed during the kick off meeting | UNIOS | M1 |
|  | Project website will be designed, hosted and managed by University of Jordan | UJ | M2 |
|  | Facebook page will be created and managed by University of Jordan Partners will post all their activities on this page | UJ and all | M2 |
|  | Promotional Materials will be designed | UNIOS | M2 |
|  | WP leader will set a detailed plan for the WP with due dates, it will include plans for three parts - Dissemination, - Sustainability and, - Networking. | UNIOS | M3 |
|  | A project description with a link of the project website will be presented in all consortium partners main institution website. | All | M3 |
|  | Creating a Network of Arts Therapists, Community Support professionals, and other stakeholders. The Network members will be involved in different activities of the project. | All | M12 |
|  | E-Learning platform will be created and managed by University of Jordan All partners will use it to teach the art therapy course during the pilot phase | UJ | M12 |
|  | Two national dissemination workshops and 1 information seminar will be organized in Jordan and Tunisia | INU USFAX | M12 |
|  | A three-day Final dissemination conference will be held at University of Jordan | UJ All | M36 |
|  | Biannual electronic newsletters will be prepared | First issue by UJ Other will be distributed among partners | M6, M12, M18, M24, M30, M36 |
|  | Progress report to be provided by WP leader every 6 months based on collected feedback from Co-Leaders | UNIOS INU USFAX | M6, M12, M18, M24, M30, M36 |

### WP 7:	Project Coordination

| Major Activities | Leader | Co- Leader | Other partners involved | Estimated Start\End Date |  |
| --- | --- | --- | --- | --- | --- |
| Task 7.1: Kick-off Meeting | UJ | - | All Partners |  | M2 |
| Task 7.2: Steering Committee |  |  |  | M2 | M36 |
| Task 7.3: Technical and Scientific Committee |  |  |  | M2 | M36 |
| Task 7.4: Biannual progress reports |  |  |  | M6 | M36 |
| Task 7.5: Operational Staff |  |  |  | M1 | M36 |

Prof. Ahmed Al- Salaymeh, presented the tasks and activities of this work package and the action plan HEALING Project coordination. The partners agreed on the following:

| No. | Task | Responsibility | Due Date |
| --- | --- | --- | --- |
|  | A Steering Committee (SC) will be established during the kick-off meeting with 1 representative from each partner | All | M1 |
|  | A Technical and Scientific Committee (TSC) will be established during the kick-off meeting with 1 representative from each partner | All | M1 |
|  | Six coordination meetings will be conducted in Amman, Athens, Brescia, Brussels, Porto, and Sousse Monthly virtual status meetings via web-conferencing Regular communication will be conducted by e-mail and shared electronic database | UJ | M1-M36 |
|  | Progress report to be provided by WP leader every 6 months based on collected feedback from Co-Leaders | UJ | M6, M12, M18, M24, M30, M36 |
|  | Meeting with Tunisian partners to discuss the Financial Management | UJ TU partners | Mar 24, 2020 2:00 PM Amman Time |
|  | Next online meeting | All | April 16, 2020 11:00 AM Amman Time |

Finally, Prof. Ahmed Al-Salaymeh Thanked all participants in the conducted online meeting and scheduled the second online meeting that will be on 16th of April, 2020.