ERASMUS+ PROGRAMME

Project Number: 610134-EPP-1-2019-1-JO-EPPKA2-CBHE-JP

HEALING:

Developing a Multidisciplinary Diploma on Art Therapy in Health Education

Minutes of

HEALING Third Online Meeting

The University of Jordan

Amman-Jordan

July 14, 2020

ERASMUS+ PROGRAMME

Project Number: 610134-EPP-1-2019-1-JO-EPPKA2-CBHE-JP

HEALING:

Developing a Multidisciplinary Diploma on Art Therapy in Health Education

Minutes of

HEALING Third Online Meeting

The University of Jordan

Amman-Jordan

July 14, 2020

Participant List

| No. | Participant Name | Position |
| --- | --- | --- |
| The University of Jordan |  |  |
|  | Prof. Ahmed Al-Salaymeh | Project Coordinator and Professor at the School of Engineering. |
|  | Prof. Rami Haddad | Dean of the Art and Design School |
|  | Eng. Leena Marashdeh | Research Assistant |
|  | Ms. Hanan Hasan | Research Assistant |
|  | Eng. Rasha Al-Baik | Research Assistant |
|  | Eng. Narees Melhem | Research Assistant |
| The Hashemite University |  |  |
|  | Dr. Aiman Al Sharei | Associate professor at the School of Medicine |
|  | Dr. Mamoon Obeidat | Assistant professor at Prince Al-Hussein bin Abdullah II Faculty of Information Technology |
| Irbid National University |  |  |
|  | Prof. Ahmad Odat | President Assistant of Irbid National University and Professor at School of Information technology |
| Jordan University of Science and Technology |  |  |
|  | Prof. Fahmi Abu Al-Rub | Professor and Contact person |
|  | Dr. Mohammad Nazzal | Faculty member at Department of Allied Medical Sciences |
| Israa University |  |  |
|  | Dr. Ghaida Abu Rumman | President Assistant and Director of Training continuous Education and Community Service Centre |
|  | Dr. Rasmieh Emmar | Faculty member |
|  | Dr. Wafeqah Althaher | Faculty member |
| University of Gabes |  |  |
|  | Dr. Mehdi Khouja | Assistant Professor at Higher Institute of Computer and Multimedia |
|  | Dr. Mohamed Ouwais Kabaou | Associate professor in Computer Science , Head of E-Learning Department |
| University of Sfax |  |  |
|  | Dr. Ismail Bouassida | Associate professor in Computer Science |
| University of Sousse |  |  |
|  | Dr. Wassim Jomaa | Associate Professor at Higher Institute of Musicology |
| University of Brescia |  |  |
|  | Dr. Giovanni Mirabella | Associate Professor of physiology |
| Porto Polytechnic |  |  |
|  | Dr. Carlos Vaz de Carvalho | Associate Professor in the Computer Engineering Department |
| National and Kapodistrian University of Athens |  |  |
|  | Dr. Sofia Papakonstantinou | Team Member |
|  | Dr. Konstantina (Nadia) Tsoli | Assistant Professor at the Department of Primary Education (NKUA) |
| Universidade Católica Portuguesa |  |  |
|  | Prof. Luís Teixeira | Assistant professor at School of Arts |
|  | Dr. Rosa Carla Silva | Assistant Professor |
| University of Osijek |  |  |
|  | Dr. Antonija Matic | Head of the Office for EU Projects and Programs |
| University College Limburg vzw |  |  |
|  | Ms. Nele Keltchtermans | Researcher |

# Minutes of the Meeting

The meeting was conducted via zoom video conferencing from 06:00 PM to 07:15 PM.

The meeting started by a welcome from the Project Coordinator, Prof. Ahmed Al-Salaymeh.

Work package leaders presented the progress in four work packages of HEALING Project (WP1, WP4, WP5, WP6), also they pointed out what is required from partners as follow:

Ms. Nele Keltchtermans (UCLL) presented the progress within “WP1: In-depth analyses of the overall situation on the on Art Therapy in Education”. The analyses report was presented and discussed partners. The following were agreed on:

| No. | Task | Responsibility | Due Date |
| --- | --- | --- | --- |
|  | Normalize the data (convert to percentage instead of numbers) to be compared with each other | UCLL INU US | July 21, 2020 |
|  | Submit the modified report | UCLL | July 21, 2020 |
|  | Form a subcommittee to meet and summarize the suggested courses for HEALING diploma based on WP1 report | Dr. Giovanni Mirabella (UNIBS) Prof. Rami Haddad (UJ) Prof. Mohammad Nazzal (JUST) Dr. Wassim Jomaa (US) Dr. Chloe Mentens (UCLL) | July 23, 2020 6:00 pm |
|  | Progress report to be provided by WP leader for the first six months | UCLL INU US | July 30, 2020 |

Dr. Carlos Vaz de Carvalho (IPP) discussed “WP4: Development of the Art Therapy Centre to support the new curriculum” with partners and the following were agreed on:

| No. | Task | Responsibility | Due Date |
| --- | --- | --- | --- |
|  | Provide a list of essential components of art therapy center | IPP | July 21, 2020 |
|  | Prepare a form to be filled by partners about the needed equipment for art therapy center | IPP | July 21, 2020 |
|  | Send the list of needed equipment to WP leader | JO partners TU partners | Aug, 2020 |

Dr. Sofia Papakonstantinou (NKUA) presented the progress in “WP5: Quality Control and Monitoring (QC&M)”. The Quality and Monitoring plan and Quality tools are ready. The following were agreed on:

| No. | Task | Responsibility | Due Date |
| --- | --- | --- | --- |
|  | WP leaders will prepare progress reports using the provided template for the following work packages: - WP1 - WP5 - WP6 - WP7 | WP leaders | July 30, 2020 |

Dr. Antonija Matic (UNIOS), presented the progress in “WP 6: Dissemination & Exploitation, Josip Juraj Strossmayer University of Osijek”, and the following were agreed on:

| No. | Task | Responsibility | Due Date |
| --- | --- | --- | --- |
|  | Check Modified dissemination plan and dissemination material | All partners | July 21, 2020 |
|  | First issue of newsletter to introduce project for stakeholders and others | UNIOS | July 31, 2020 |

Finally, Prof. Ahmed Al-Salaymeh Thanked all participants in the conducted online meeting and scheduled the Fifth online meeting to be next month at 6:00 PM Jordan Time.