**ERASMUS+ PROGRAMME**

**Project Number: 610134-EPP-1-2019-1-JO-EPPKA2-CBHE-JP**

**HEALING:**

**Developing a Multidisciplinary Diploma on Art Therapy in Health Education**

**Minutes of**

**HEALING Second Online Meeting**

**The University of Jordan**

**Amman-Jordan**

**April 16, 2020**

**Participant List**

|  |  |  |
| --- | --- | --- |
| **No.** | **Participant Name** | **Position** |
| **The University of Jordan** | | |
|  | Prof. Ahmed Al-Salaymeh | Project Coordinator and Professor at the School of Engineering. |
|  | Prof. Rami Haddad | Dean of School of Arts |
|  | Prof. Mohammad AlShraideh | Dean of the School of Graduate Studies |
|  | Eng. Leena Marashdeh | Research Assistant |
|  | Ms. Hanan Hasan | Research Assistant |
|  | Eng. Rasha Al-Beek | Research Assistant |
| **The Hashemite University** | | |
|  | Dr. Aiman Al Sharei | Associate professor at the School of Medicine |
|  | Prof. Aman Khasawneh | Faculty member at Faculty of Physical Education and Sport Sciences |
|  | Dr. Mamoon Obeidat | Assistant professor at Prince Al-Hussein bin Abdullah II Faculty of Information Technology |
| **Irbid National University** | | |
|  | Prof. Ahmad Khasawneh | President of Irbid National University |
|  | Prof. Ahmad Odat | President Assistant of Irbid National University and Professor at School of Information technology |
| **Jordan University of Science and Technology** | | |
|  | Dr. Mohammad Nazzal | Faculty member at Department of Allied Medical Sciences |
|  | Eng. Ruba Hasan | Research Assistant |
| **Israa University** | | |
|  | Dr. Ghaida Abu Rumman | President Assistant and Director of Training continuous Education and Community Service Centre |
|  | Dr. Rasmieh Emmar | Faculty member |
|  | Dr. Wafeqah Althaher | Faculty member |
| **University of Gabes** | | |
|  | Dr. Mehdi Khouja | Assistant Professor at Higher Institute of Computer and Multimedia |
|  | Dr. Mohamed Ouwais Kabaou | Associate professor in Computer Science , Head of E-Learning Department |
|  | Dr. Hela Hassine | Assistant Professor in Science and Techniques of Art at Higher Institute of Computer Sciences and multimedia |
| **University of Sfax** | | |
|  | Dr. Ismail Bouassida | Associate professor in Computer Science |
| **University of Sousse** | | |
|  | Dr. Wassim Jomaa | Associate Professor at Higher Institute of Musicology |
|  | Dr. Adel Bouallegue | Associate Professor |
| **University of Brescia** | | |
|  | - | - |
| **Porto Polytechnic** | | |
|  | Dr. Carlos Vaz de Carvalho | Associate Professor of the Computer Engineering Department |
| **National and Kapodistrian University of Athens** | | |
|  | Dr. Sofia Papakonstantinou | Team Member |
|  | Dr Konstantina (Nadia) Tsoli | Assistant Professor at the Department of Primary Education (NKUA) |
| **Universidade Católica Portuguesa** | | |
|  | Luís Teixeira | Assistant professor at School of Arts |
|  | Luis Sá | Assistant professor at Institute of Health Sciences |
| **University of Osijek** | | |
|  | Prof. Berislav Jerkovic | Head of Music department |
|  | Prof. Antoaneta Radocaj | Professor at Osijek Art Academy |
|  | Dr. Antonija Matic | Head of the Office for EU Projects and Programs |
| **University College Limburg vzw** | | |
|  | Ms. Chloe Mentens | Researcher |
|  | Ms. Nele Keltchtermans | Researcher |

# Minutes of the Meeting

The meeting was conducted via zoom video conferencing from 11:00 AM to 12:30 PM.

The meeting started by a welcome from the Project Coordinator, Prof. Ahmed Al-Salaymeh.

**Prof. Ahmed Al-Salaymeh** (UJ) presented HEALING Project in Brief, he presented the project progress in different work packages according to the set plans in the minutes of meeting.

|  |  |  |  |
| --- | --- | --- | --- |
| No. | Task | Responsibility | Due Date |
|  | Assign members for different committees:   * Steering Committee Members * Scientific Committee Members * Quality Committee Members * Dissemination Committee Members | UCP  UCLL | ASAP |
|  | Quality WP leader will prepare a summary table that include all quality activities, deliverables of the project and their method of evaluation with their quality indicators | NKUA | April 23, 2020 |
|  | Design electronic Promotional Material:   * Brochure * Roll up Banner * …… | UNIOS  UJ | April 30, 2020 |
|  | Partners will post their activities and useful articles on HEALING Facebook page: <https://www.facebook.com/Healing-Project-101788921457020/> | All | Periodically |
|  | Dissemination WP leader will set a detailed plan for the WP with due dates, it will include plans for three parts   * Dissemination, * Sustainability and, * Networking. | UNIOS | April 30, 2020 |
|  | Post a project description with a link of the project website in partners main institution website. | All | April 30, 2020 |

**Dr. Chloe Mentens** (UCLL) presented the draft surveys within “**WP1: In-depth analyses of the overall situation on the on Art Therapy in Education**” and the following tasks were agreed on:

|  |  |  |  |
| --- | --- | --- | --- |
| No. | Task | Responsibility | Due Date |
|  | Review the surveys and send comments via email | Scientific committee  Quality Committee | Before April 22, 2020 |
|  | Provide list of offered courses in other partner universities to be included in the choices of the survey | US  UNIOS  UNIBS | Before April 22, 2020 |
|  | Meeting to finalize the surveys | UCLL  INU  US  Scientific committee  Quality Committee | April 22, 2020 |
|  | Start collecting responses | JO partners  TU partners | April 26-May 31, 2020 |
|  | The surveys will be analyzed, and the final report including the three surveys analysis will be prepared | UCLL  INU  US | June 15, 2020 |
|  | Progress report to be provided by WP leader every 6 months based on collected feedback from Co-Leaders | UCLL  INU  US | M6, M12 |

**Finally, Prof. Ahmed Al-Salaymeh Thanked all participants in the conducted online meeting and scheduled the third online meeting to be on June 4, 2020 at 6:00 PM.**