**ERASMUS+ PROGRAMME**

**Project Number: 610134-EPP-1-2019-1-JO-EPPKA2-CBHE-JP**

**HEALING:**

**Developing a Multidisciplinary Diploma on Art Therapy in Health Education**

**Minutes of**

**HEALING Third Online Meeting**

**The University of Jordan**

**Amman-Jordan**

**June 4, 2020**

**Participant List**

|  |  |  |
| --- | --- | --- |
| **No.** | **Participant Name** | **Position** |
| **The University of Jordan**  |
|  | Prof. Ahmed Al-Salaymeh | Project Coordinator and Professor at the School of Engineering. |
|  | Prof. Mohammad AlShraideh | Dean of the School of Graduate Studies  |
|  | Eng. Leena Marashdeh | Research Assistant |
|  | Ms. Hanan Hasan  | Research Assistant |
|  | Eng. Narees Melhem | Research Assistant |
| **The Hashemite University** |
|  | Dr. Aiman Al Sharei | Associate professor at the School of Medicine |
|  | Prof. Aman Khasawneh | Faculty member at Faculty of Physical Education and Sport Sciences |
|  | Dr. Mamoon Obeidat | Assistant professor at Prince Al-Hussein bin Abdullah II Faculty of Information Technology |
| **Irbid National University** |
|  | Prof. Ahmad Khasawneh  | President of Irbid National University |
|  | Prof. Ahmad Odat | President Assistant of Irbid National University and Professor at School of Information technology |
| **Jordan University of Science and Technology**  |
|  | Prof. Fahmi Abu Al-Rub | Professor and Contact person |
|  | Dr. Mohammad Nazzal | Faculty member at Department of Allied Medical Sciences |
|  | Eng. Ruba Hasan | Research Assistant  |
| **Israa University**  |
|  | Dr. Ghaida Abu Rumman | President Assistant and Director of Training continuous Education and Community Service Centre  |
|  | Prof. Aiman Al Garrallah | Dean ​of Educational Science |
|  | Dr. Rasmieh Emmar | Faculty member |
|  | Dr. Wafeqah Althaher | Faculty member |
|  | Dr. Alaa Abu Al-Rub | Head of physical Therapy Department |
|  | Dr. Intesar Tannous | Faculty member at Faculty of  |
| **University of Gabes** |
|  | Dr. Mehdi Khouja | Assistant Professor at Higher Institute of Computer and Multimedia  |
|  | Dr. Mohamed Ouwais Kabaou | Associate professor in Computer Science , Head of E-Learning Department  |
|  | Dr. Hela Hassine | Assistant Professor in Science and Techniques of Art at Higher Institute of Computer Sciences and multimedia  |
| **University of Sfax** |
|  | Dr. Ismail Bouassida | Associate professor in Computer Science |
| **University of Sousse** |
|  | Dr. Wassim Jomaa | Associate Professor at Higher Institute of Musicology  |
|  | Dr. Adel Bouallegue | Associate Professor |
| **University of Brescia** |
|  | Dr. Giovanni Mirabella | Associate Professor of physiology |
| **Porto Polytechnic** |
|  | Dr. Carlos Vaz de Carvalho | Associate Professor in the Computer Engineering Department |
|  | Dr. Ana Barata | Professor at IPP-ISEP |
| **National and Kapodistrian University of Athens** |
|  | Dr. Sofia Papakonstantinou | Team Member |
|  | Dr Konstantina (Nadia) Tsoli | Assistant Professor at the Department of Primary Education (NKUA) |
| **Universidade Católica Portuguesa** |
|  | Prof. Luís Teixeira | Assistant professor at School of Arts |
|  | Prof. Luis Sá | Assistant professor at Institute of Health Sciences |
|  | Dr. Mariana Barbosa | Assistant Professor at the Faculty of Education and Psychology |
|  | Dr. Rosa Carla Silva | Assistant Professor |
| **University of Osijek** |
|  | Prof. Berislav Jerkovic | Head of Music department |
|  | Prof. Antoaneta Radocaj  | Professor at Osijek Art Academy |
|  | Dr. Antonija Matic | Head of the Office for EU Projects and Programs  |
| **University College Limburg vzw** |
|  | Ms. Chloe Mentens | Researcher  |
|  | Ms. Nele Keltchtermans | Researcher |

# Minutes of the Meeting

The meeting was conducted via zoom video conferencing from 06:00 PM to 07:15 PM.

The meeting started by a welcome from the Project Coordinator, Prof. Ahmed Al-Salaymeh.

**Work package leaders** presented the progress in three work packages of HEALING Project, also they pointed out what is required from partners as follow:

**Dr. Chloe Mentens** (UCLL) presented the progress in filling the surveys within “**WP1: In-depth analyses of the overall situation on the on Art Therapy in Education**”, the collected responses are still under the target numbers. The following were agreed on:

|  |  |  |  |
| --- | --- | --- | --- |
| No. | Task | Responsibility | Due Date |
|  | Extend the due date for collecting responses by two weeks | JO partnersTU partners | June 15, 2020 |
|  | Survey analysis will be done by Co-leaders, final analysis report will be submitted by WP leader | UCLLINUUS | June 30, 2020 |
|  | Progress report to be provided by WP leader every 6 months based on collected feedback from Co-Leaders | UCLLINUUS | M6, M12 |

**Dr. Sofia Papakonstantinou** (NKUA) presented the progress in “**WP5: Quality Control and Monitoring (QC&M)**”. The Quality and Monitoring plan and Quality tools are ready. The following were agreed on:

|  |  |  |  |
| --- | --- | --- | --- |
| No. | Task | Responsibility | Due Date |
|  | A google drive for the Project deliverables has been created and shared with partners. Project documents will be uploaded to the folder. <https://drive.google.com/drive/folders/1ohqbzyjoUT90eRF4kVuOkBWGdqMrTvow?usp=sharing>  | Partners | - |
|  | Following deliverables should be evaluated using a specific evaluation form prepared by WP leader in the coming six-month period:* Final Report of WP1
* Report on selected courses to be designed/ updated within WP2
* Quality & Monitoring Plan
* Dissemination plan
* Project Website
* Promotional material
* Dissemination workshops
* Project Transnational Meetings
 | Scientific Committee members Dissemination Committee | Next Six-month period  |
|  | Work package leader will send partners reminders to fill the evaluation forms. | NKUA | After deliverables and meeting |
|  | WP leaders will prepare progress reports for each WP based on feedback from partners.  | WP leaders | Every 6 months |

**Dr. Antonija Matic (UNIOS),** presented the progress in “**WP 6: Dissemination & Exploitation, Josip Juraj Strossmayer University of Osijek**”. The dissemination plan and material were prepared and distributed to partners for review and comments.

|  |  |  |  |
| --- | --- | --- | --- |
| No. | Task | Responsibility | Due Date |
|  | Modify the prepared dissemination plan and material according to partners comments  | WP leader | June, 2020 |
|  | Each partner to provide a Facebook account to be assigned as editor for HEALING project page on Facebook for publishing project activities at their universitiesFacebook Page: <https://www.facebook.com/Healing-Project-101788921457020/>  | Partners | June, 2020 |
|  | First issue of newsletter to introduce project for stakeholders and others Next issues will be distributed between partners in the next meeting | WP leader | June, 2020 |

**Finally, Prof. Ahmed Al-Salaymeh Thanked all participants in the conducted online meeting and scheduled the Fourth online meeting to be on July 7, 2020 at 6:00 PM Jordan Time.**