**ERASMUS+ PROGRAMME**

**Project Number: 610134-EPP-1-2019-1-JO-EPPKA2-CBHE-JP**

**HEALING:**

**Developing a Multidisciplinary Diploma on Art Therapy in Health Education**

**Minutes of**

**HEALING Third Online Meeting**

**The University of Jordan**

**Amman-Jordan**

**July 14, 2020**

**Participant List**

|  |  |  |
| --- | --- | --- |
| **No.** | **Participant Name** | **Position** |
| **The University of Jordan**  |
|  | Prof. Ahmed Al-Salaymeh | Project Coordinator and Professor at the School of Engineering. |
|  | Prof. Rami Haddad | Dean of the Art and Design School  |
|  | Eng. Leena Marashdeh | Research Assistant |
|  | Ms. Hanan Hasan  | Research Assistant |
|  | Eng. Rasha Al-Baik | Research Assistant |
|  | Eng. Narees Melhem | Research Assistant |
| **The Hashemite University** |
|  | Dr. Aiman Al Sharei | Associate professor at the School of Medicine |
|  | Dr. Mamoon Obeidat | Assistant professor at Prince Al-Hussein bin Abdullah II Faculty of Information Technology |
| **Irbid National University** |
|  | Prof. Ahmad Odat | President Assistant of Irbid National University and Professor at School of Information technology |
| **Jordan University of Science and Technology**  |
|  | Prof. Fahmi Abu Al-Rub | Professor and Contact person |
|  | Dr. Mohammad Nazzal | Faculty member at Department of Allied Medical Sciences |
| **Israa University**  |
|  | Dr. Ghaida Abu Rumman | President Assistant and Director of Training continuous Education and Community Service Centre  |
|  | Dr. Rasmieh Emmar | Faculty member |
|  | Dr. Wafeqah Althaher | Faculty member |
| **University of Gabes** |
|  | Dr. Mehdi Khouja | Assistant Professor at Higher Institute of Computer and Multimedia  |
|  | Dr. Mohamed Ouwais Kabaou | Associate professor in Computer Science , Head of E-Learning Department  |
| **University of Sfax** |
|  | Dr. Ismail Bouassida | Associate professor in Computer Science |
| **University of Sousse** |
|  | Dr. Wassim Jomaa | Associate Professor at Higher Institute of Musicology  |
| **University of Brescia** |
|  | Dr. Giovanni Mirabella | Associate Professor of physiology |
| **Porto Polytechnic** |
|  | Dr. Carlos Vaz de Carvalho | Associate Professor in the Computer Engineering Department |
| **National and Kapodistrian University of Athens** |
|  | Dr. Sofia Papakonstantinou | Team Member |
|  | Dr. Konstantina (Nadia) Tsoli | Assistant Professor at the Department of Primary Education (NKUA) |
| **Universidade Católica Portuguesa** |
|  | Prof. Luís Teixeira | Assistant professor at School of Arts |
|  | Dr. Rosa Carla Silva | Assistant Professor |
| **University of Osijek** |
|  | Dr. Antonija Matic | Head of the Office for EU Projects and Programs  |
| **University College Limburg vzw** |
|  | Ms. Nele Keltchtermans | Researcher |

# Minutes of the Meeting

The meeting was conducted via zoom video conferencing from 06:00 PM to 07:15 PM.

The meeting started by a welcome from the Project Coordinator, Prof. Ahmed Al-Salaymeh.

**Work package leaders** presented the progress in four work packages of HEALING Project (WP1, WP4, WP5, WP6), also they pointed out what is required from partners as follow:

**Ms. Nele Keltchtermans** (UCLL) presented the progress within “**WP1: In-depth analyses of the overall situation on the on Art Therapy in Education**”. The analyses report was presented and discussed partners. The following were agreed on:

|  |  |  |  |
| --- | --- | --- | --- |
| No. | Task | Responsibility | Due Date |
|  | Normalize the data (convert to percentage instead of numbers) to be compared with each other | UCLLINUUS | July 21, 2020 |
|  | Submit the modified report  | UCLL | July 21, 2020 |
|  | Form a subcommittee to meet and summarize the suggested courses for HEALING diploma based on WP1 report | Dr. Giovanni Mirabella (UNIBS)Prof. Rami Haddad (UJ) Prof. Mohammad Nazzal (JUST)Dr. Wassim Jomaa (US)Dr. Chloe Mentens (UCLL) | July 23, 20206:00 pm |
|  | Progress report to be provided by WP leader for the first six months  | UCLLINUUS | July 30, 2020 |

**Dr. Carlos Vaz de Carvalho (IPP)** discussed “**WP4: Development of the Art Therapy Centre to support the new curriculum”** with partners and the following were agreed on:

|  |  |  |  |
| --- | --- | --- | --- |
| No. | Task | Responsibility | Due Date |
|  | Provide a list of essential components of art therapy center  | IPP | July 21, 2020 |
|  | Prepare a form to be filled by partners about the needed equipment for art therapy center  | IPP | July 21, 2020 |
|  | Send the list of needed equipment to WP leader | JO partnersTU partners  | Aug, 2020 |

**Dr. Sofia Papakonstantinou** (NKUA) presented the progress in “**WP5: Quality Control and Monitoring (QC&M)**”. The Quality and Monitoring plan and Quality tools are ready. The following were agreed on:

|  |  |  |  |
| --- | --- | --- | --- |
| No. | Task | Responsibility | Due Date |
|  | WP leaders will prepare progress reports using the provided template for the following work packages:* WP1
* WP5
* WP6
* WP7
 | WP leaders | July 30, 2020 |

**Dr. Antonija Matic (UNIOS),** presented the progress in “**WP 6: Dissemination & Exploitation, Josip Juraj Strossmayer University of Osijek**”, and the following were agreed on:

|  |  |  |  |
| --- | --- | --- | --- |
| No. | Task | Responsibility | Due Date |
|  | Check Modified dissemination plan and dissemination material  | All partners | July 21, 2020 |
|  | First issue of newsletter to introduce project for stakeholders and others  | UNIOS | July 31, 2020 |

**Finally, Prof. Ahmed Al-Salaymeh Thanked all participants in the conducted online meeting and scheduled the Fifth online meeting to be next month at 6:00 PM Jordan Time.**