**ERASMUS+ PROGRAMME**

**Project Number: 610134-EPP-1-2019-1-JO-EPPKA2-CBHE-JP**

**HEALING:**

**Developing a Multidisciplinary Diploma on Art Therapy in Health Education**

**Minutes of**

**HEALING Fifth Online Meeting**

**The University of Jordan**

**Amman-Jordan**

**September 21, 2020**

**Participant List**

|  |  |  |
| --- | --- | --- |
| **No.** | **Participant Name** | **Position** |
| **The University of Jordan** | | |
|  | Prof. Ahmed Al-Salaymeh | Project Coordinator and Professor at the School of Engineering. |
|  | Prof. Rami Haddad | Dean of the Art and Design School |
|  | Prof. Mohammad Al-Shraideh | Dean of the School of Graduate Studies |
|  | Dr. Zaid AlKayed | Psychiatry resident at University of Jordan Hospital |
|  | Eng. Rasha Al-Baik | Research Assistant |
|  | Ms. Hanan Hasan | Research Assistant |
|  | Eng. Narees Melhem | Research Assistant |
| **The Hashemite University** | | |
|  | Dr. Aiman Al Sharei | Associate professor at the School of Medicine |
|  | Dr. Mamoon Obeidat | Assistant professor at Prince Al-Hussein bin Abdullah II Faculty of Information Technology |
| **Irbid National University** | | |
|  | Prof. Ahmad Odat | President Assistant of Irbid National University and Professor at School of Information technology |
| **Jordan University of Science and Technology** | | |
|  | Prof. Fahmi Abu Al-Rub | Professor and Contact person |
|  | Dr. Mohammad Nazzal | Faculty member at Department of Allied Medical Sciences |
| **Israa University** | | |
|  | Dr. Ghaida Abu Rumman | President Assistant and Director of Training continuous Education and Community Service Centre |
|  | Dr. Rasmieh Emmar | Faculty member |
|  | Dr. Intesar Tannous | Faculty member |
| **University of Gabes** | | |
|  | Dr. Hela Hassine | Assistant Professor in Science and Techniques of Art at Higher Institute of Computer Sciences and multimedia |
| **University of Sfax** | | |
|  | Dr. Ismail Bouassida | Associate professor in Computer Science |
|  | Dr. Slim Kallel | Associate professor in Computer Science |
| **University of Sousse** | | |
|  | Dr. Wassim Jomaa | Associate Professor at Higher Institute of Musicology |
| **University of Brescia** | | |
|  | Dr. Giovanni Mirabella | Associate Professor of physiology |
| **Porto Polytechnic** | | |
|  | Dr. Carlos Vaz de Carvalho | Associate Professor in the Computer Engineering Department |
|  | Dr. Ana Barata | Professor at IPP-ISEP |
| **National and Kapodistrian University of Athens** | | |
|  | Dr. Sofia Papakonstantinou | Team Member |
| **Universidade Católica Portuguesa** | | |
|  | Prof. Luís Teixeira | Assistant professor at School of Arts |
|  | Prof. Luis Sá | Assistant professor at Institute of Health Sciences |
|  | Prof. Elisa Veiga | Professor at Faculty of Education and Psychology |
|  | Prof. Alexandra Carneiro | Professor at Faculty of Education and Psychology |
|  | Dr. Rosa Carla Silva | Assistant Professor |
| **University of Osijek** | | |
|  | Prof. Berislav Jerkovic | Head of Music department |
|  | Prof. Antoaneta Radocaj | Professor at Osijek Art Academy |
|  | Dr. Antonija Matic | Head of the Office for EU Projects and Programs |
| **University College Limburg vzw** | | |
|  | Ms. Chloë Mentens | Researcher |
|  | Ms. Nele Keltchtermans | Researcher |

# Minutes of the Meeting

The meeting was conducted via zoom video conferencing from 06:00 PM to 08:35 PM Amman Time.

The meeting started by a welcome from the Project Coordinator, Prof. Ahmed Al-Salaymeh.

**Work package leaders** presented the progress in seven work packages of HEALING Project (WP1, WP2, WP3, WP4, WP5, WP6 and WP7). Also they pointed out what is required from partners as follow:

### WP1: In-depth analyses of the overall situation on the on Art Therapy in Education

**Ms.** **Chloë Mentens (VZW)** presented the progress within “**WP1: In-depth analyses of the overall situation on the on Art Therapy in Education**”. The tangible output (report) was presented and discussed. The following were agreed on:

|  |  |  |  |
| --- | --- | --- | --- |
| No. | Task | Responsibility | Due Date |
|  | Send feedback on the final draft report to be finalized. | All partners | End of September |
|  | Submit the modified report | WP leader | End of September |

### WP2: Curricula Development

**Dr. Giovanni Mirabella (UNIBS), Prof. Rami Haddad (UJ) and Dr. Mohammad Nazzal (JUST)** discussed “**WP 2. Curricula Development”** with partners and the following were agreed on:

|  |  |  |  |
| --- | --- | --- | --- |
| No. | Task | Responsibility | Due Date |
|  | Arrange meeting with Dr. Giovanni and Jordanian partners to discuss study plan | Dr. Giovanni Mirabella (UNIBS)  JO partners | End of September |
|  | Arrange meeting between Dr. Giovanni, Prof. Rami (UJ) and Tunisian partners to discuss study plan | Dr. Giovanni Mirabella (UNIBS)  TU partners | End of September |
|  | Quality check on Study plans | Dr. Giovanni Mirabella (UNIBS)  Prof. Rami Haddad (UJ)  Dr. Mohammad Nazzal (JUST) | October 1st , 2020 |
|  | Submit the final study plan and get comments from all partners and Co-leaders (IU and UNIVGB) and send the final draft to TU Partners | WP leaders | October 3rd, 2020 |
|  | Form a technical committee to meet and summarize the suggested courses for HEALING diploma based on WP1 report | Dr. Giovanni Mirabella (UNIBS)  Prof. Rami Haddad (UJ)  Dr. Mohammad Nazzal (JUST)  Dr. Wassim Jomaa (US)  Dr. Chloe Mentens (UCLL) | First week of October |

### WP3: Capacity Building and Training Workshops (Teacher/Technician Staff & Students)

**Prof. Luís Teixeira** discussed “**WP 3. Development: Capacity Building and Training Workshops (Teacher/Technician Staff & Students)**” with partners. The following were agreed on:

|  |  |  |  |
| --- | --- | --- | --- |
| No. | Task | Responsibility | Due Date |
|  | Prepare a template about training qualifications for each EU partner regarding students and staff. | WP leaders | Before December |

### WP4: Development of the Art Therapy Centre to support the new curriculum

**Dr. Carlos Vaz de Carvalho,** discussed “**WP4: Development of the Art Therapy Centre to support the new curriculum**” with partners, and the following were agreed on:

|  |  |  |  |
| --- | --- | --- | --- |
| No. | Task | Responsibility | Due Date |
|  | Submit the final list of equipment from all partners as the following should be submitted   1. List of Equipment 2. Specifications 3. Justifications (Connect the equipment use with HEALING objectives, WP1 and WP2 results) | ALL JO and TN Partners  WP leader | End of September |

### WP5: Quality Control and Monitoring (QC&M)

**Dr. Sofia Papakonstantinou,** discussed “**WP5: Quality Control and Monitoring (QC&M)**” with partners, and the following were agreed on:

|  |  |  |  |
| --- | --- | --- | --- |
| No. | Task | Responsibility | Due Date |
|  | Send the evaluation link for 4th of June meeting to UJ and INU to be filled from Participants | WP leader | September 23, 2020 |
|  | Send the evaluation link for 5th meeting to all partners to be filled from Participants | WP leader | September 30, 2020 |

### WP 6: Dissemination & Exploitation

**Dr. Antonija Matic (UNIOS),** discussed “**WP 6: Dissemination & Exploitation**” with partners, and the following were agreed on:

|  |  |  |  |
| --- | --- | --- | --- |
| No. | Task | Responsibility | Due Date |
|  | Send the biannual table for E-Newsletter responsibility to WP leader | Eng. Rasha | September 22th , 2020 |
|  | Follow up with Next E-Newsletter with responsible institution | WP leader | At the end of this year |
|  | Collect Biannual Dissemination Activities reports from all partners | WP leader | End of October |

### WP 7: Project Coordination

**Eng. Rasha Al-Beek and Ms. Hanan Hasan from UJ,** presented financial management instructions regarding staff cost category with JO and TU partners “**WP7: Project Coordination**”, and the following were agreed on:

|  |  |  |  |
| --- | --- | --- | --- |
| No. | Task | Responsibility | Due Date |
|  | Send the filled table of days distribution to JO and TU partners to fill it with needed information as mentioned in the meeting by Eng. Rasha | JO and TU | End of September |

**Finally, Prof. Ahmed Al-Salaymeh expressed his thankful to all participants in the conducted online meeting and scheduled the sixth SC online meeting to be next month October 20,2020.**

**Meeting Recording Link:**

<https://zoom.us/rec/share/5mp8wE3seuy6tkeFzhR45f7Uf3Ol9D3WiiX2fLMPq4XIpx-D4AZNLe4fZSNkhKso.8R0E5_REgOAg48sm?startTime=1600700012000>

**Access Passcode:** MG?2y%QS