**ERASMUS+ PROGRAMME**

**Project Number: 610134-EPP-1-2019-1-JO-EPPKA2-CBHE-JP**

**HEALING:**

**Developing a Multidisciplinary Diploma on Art Therapy in Health Education**

**Minutes of**

**HEALING Sixth Online Meeting**

**The University of Jordan**

**Amman-Jordan**

**December 17th, 2020**

**Participant List**

|  |  |  |
| --- | --- | --- |
| **No.** | **Participant Name** | **Position** |
| **The University of Jordan** | | |
|  | Prof. Ahmed Al-Salaymeh | Project Coordinator and Professor at the School of Engineering. |
|  | Prof. Rami Haddad | Dean of the Art and Design School |
|  | Prof. Mohammad Al-Shraideh | Dean of the School of Graduate Studies |
|  | Ms. Joyce Raie | Assistant Dean of the Art and Design School |
|  | Eng. Rasha Al-Baik | Research Assistant |
|  | Ms. Hanan Hasan | Research Assistant |
| **The Hashemite University** | | |
|  | Dr. Aiman Al Sharei | Associate professor at the School of Medicine |
|  | Dr. Mamoon Obeidat | Assistant professor at Prince Al-Hussein bin Abdullah II Faculty of Information Technology |
|  | Prof. Aman Khasawneh | Faculty member at Faculty of Physical Education and Sport Sciences |
| **Irbid National University** | | |
|  | Prof. Ahmad Odat | President Assistant of Irbid National University and Professor at School of Information technology |
| **Jordan University of Science and Technology** | | |
|  | Dr. Mohammad Nazzal | Faculty member at Department of Allied Medical Sciences |
|  | Eng. Ruba Hasan | Team member of Healing project at JUST |
| **Israa University** | | |
|  | Dr. Ghaida Abu Rumman | President Assistant and Director of Training continuous Education and Community Service Centre |
|  | Dr. Rasmieh Emmar | Faculty member |
|  | Dr. Intesar Tannous | Faculty member |
|  | Dr. Salameh Aldajah | Faculty member |
|  | Dr. Wafika Thaher | Faculty member |
|  | Dr. Alaa Abu Alrub | Faculty member |
| **University of Gabes** | | |
|  | Dr. Mehdi Khouja | Assistant Professor at Higher Institute of Computer and Multimedia |
|  | Dr. Mohamed Ouwais Kabaou | Associate professor in Computer Science , Head of E-Learning Department |
| **University of Sfax** | | |
|  | Dr. Ismail Bouassida | Associate professor in Computer Science |
|  | Dr. Amine Elleuch | Associate Professor |
| **University of Sousse** | | |
|  | Dr. Wassim Jomaa | Associate Professor at Higher Institute of Musicology |
|  | Dr. Adel Bouallegue | Associate Professor |
| **University of Brescia** | | |
|  | Dr. Giovanni Mirabella | Associate Professor of physiology |
| **Porto Polytechnic** | | |
|  | Dr. Carlos Vaz de Carvalho | Associate Professor in the Computer Engineering Department |
| **National and Kapodistrian University of Athens** | | |
|  | Dr. Sofia Papakonstantinou | Team Member |
|  | Dr Konstantina (Nadia) Tsoli | Assistant Professor at the Department of Primary Education (NKUA) |
| **Universidade Católica Portuguesa** | | |
|  | Prof. Luís Teixeira | Assistant professor at School of Arts |
|  | Prof. Luis Sá | Assistant professor at Institute of Health Sciences |
| **University of Osijek** | | |
|  | Dr. Antonija Matic | Head of the Office for EU Projects and Programs |
| **University College Limburg vzw** | | |
|  | Ms. Chloë Mentens | Researcher |

# Minutes of the Meeting

The meeting was conducted via zoom video conferencing from 01:00 PM to 03:30 PM Amman Time.

The meeting started by a welcome from the Project Coordinator, Prof. Ahmed Al-Salaymeh.

**Work package leaders** presented the progress in the work packages of HEALING Project (WP2, WP3, WP4, WP5, WP6 and WP7). Also they pointed out what is required from partners as follow:

### WP2: Curricula Development

**Dr. Giovanni Mirabella (UNIBS), Prof. Rami Haddad (UJ) and Dr. Aiman AlShara’ (HU)** discussed “**WP 2. Curricula Development”** with partners and the following were agreed on:

|  |  |  |  |
| --- | --- | --- | --- |
| No. | Task | Responsibility | Due Date |
|  | Arrange a meeting with Dr. Giovanni and Project coordinator with Co leaders to prepare road map for courses preparation.   * Collect the expertise of each institution. * prepare a plan to prepare course outline template with learning outcomes and by (Professional, Vocational, Master, Training Courses …). * Creation of committees responsible to develop the selected courses. | Dr. Giovanni Mirabella (UNIBS), IU, UNIGVB. | Before End of December, 2020 |
|  | Final Study plans (Final Version) should be submitted to Dr. Giovanni. | Eng. Rasha AlBeek | When receiving from JO and TU partners 31.12.2020 |
|  | Art therapy accreditation starting process | JO, TU | During Jan, 2021 |

### WP3: Capacity Building and Training Workshops (Teacher/Technician Staff & Students)

**Prof. Luís Teixeira** discussed “**WP 3. Development: Capacity Building and Training Workshops (Teacher/Technician Staff & Students)**” with partners. The following were agreed on:

|  |  |  |  |
| --- | --- | --- | --- |
| No. | Task | Responsibility | Due Date |
|  | Prepare a template about training qualifications for each EU partner regarding students and staff and connect it with Healing courses | WP leaders | Before End of December, 2020 |
|  | Prepare a selection criteria for training workshop regarding students and staff. | WP leaders | January, 31st 2021 |
|  | Conduct an online meeting to discuss the capacity plan and its relation to Wp2. | WP leaders and Co-leaders | Between 21.12.2020 – 07.01.2021 |
|  | Preparation for conducting Online training workshops | WP leader  EU partners | Jan, 2021 – June, 2021 |

### WP4: Development of the Art Therapy Centre to support the new curriculum

**Dr. Carlos Vaz de Carvalho,** discussed “**WP4: Development of the Art Therapy Centre to support the new curriculum**” with partners, and the following were agreed on:

|  |  |  |  |
| --- | --- | --- | --- |
| No. | Task | Responsibility | Due Date |
|  | Equipment Documents From Tunisian | TU | Before Jan, 31st 2021 |
|  | Send Art therapy centre template to JO and TU | IPP and UJ | Before Jan, 7th 2021 |

### WP5: Quality Control and Monitoring (QC&M)

**Dr. Sofia Papakonstantinou,** discussed “**WP5: Quality Control and Monitoring (QC&M)**” with partners, and the following were agreed on:

|  |  |  |  |
| --- | --- | --- | --- |
| No. | Task | Responsibility | Due Date |
|  | Send the evaluation link for 6th meeting to all partners to be filled from Participants | WP leader | One week after the meeting |
|  | Send the evaluation link from HEALING Website to all partners to be filled | WP leader | One week after the meeting |
|  | Checking the Google drive | WP leader | continuously |

### WP 6: Dissemination & Exploitation

**Dr. Antonija Matic (UNIOS),** discussed “**WP 6: Dissemination & Exploitation**” with partners, and the following were agreed on:

|  |  |  |  |
| --- | --- | --- | --- |
| No. | Task | Responsibility | Due Date |
|  | Conduct dissemination activities (online or physical). | All | Continuously |
|  | Send the dissemination collected activities for all partners. | Eng. Rasha | 31.12.2020 |
|  | Follow up with 2nd E-Newsletter with responsible institution. | WP leader + Eng. Rasha + Prof. Ahmad Odat | At the end of this year |
|  | Collect Biannual Dissemination Activities reports from all partners. | WP leader | End of January, 2021 |

### WP 7: Project Coordination

**Eng. Rasha Al-Beek from UJ,** Summarized the progress of HEALING project.

**Finally, Prof. Ahmed Al-Salaymeh expressed his thankful to all participants in the conducted online meeting and scheduled the seventh SC online meeting to be on Febreuary,2021.**

**(Next meeting date will be chosen by DOODLE)**