**ERASMUS+ PROGRAMME**

**Project Number: 610134-EPP-1-2019-1-JO-EPPKA2-CBHE-JP**

**HEALING:**

**Developing a Multidisciplinary Diploma on Art Therapy in Health Education**

**Minutes of**

**HEALING Sixth Online Meeting**

**The University of Jordan**

**Amman-Jordan**

**December 17th, 2020**

**Participant List**

|  |  |  |
| --- | --- | --- |
| **No.** | **Participant Name** | **Position** |
| **The University of Jordan**  |
|  | Prof. Ahmed Al-Salaymeh | Project Coordinator and Professor at the School of Engineering. |
|  | Prof. Rami Haddad | Dean of the Art and Design School  |
|  | Prof. Mohammad Al-Shraideh  | Dean of the School of Graduate Studies  |
|  | Ms. Joyce Raie | Assistant Dean of the Art and Design School |
|  | Eng. Rasha Al-Baik | Research Assistant |
|  | Ms. Hanan Hasan  | Research Assistant |
| **The Hashemite University** |
|  | Dr. Aiman Al Sharei | Associate professor at the School of Medicine |
|  | Dr. Mamoon Obeidat | Assistant professor at Prince Al-Hussein bin Abdullah II Faculty of Information Technology |
|  | Prof. Aman Khasawneh | Faculty member at Faculty of Physical Education and Sport Sciences |
| **Irbid National University** |
|  | Prof. Ahmad Odat | President Assistant of Irbid National University and Professor at School of Information technology |
| **Jordan University of Science and Technology**  |
|  | Dr. Mohammad Nazzal | Faculty member at Department of Allied Medical Sciences |
|  | Eng. Ruba Hasan  | Team member of Healing project at JUST |
| **Israa University**  |
|  | Dr. Ghaida Abu Rumman | President Assistant and Director of Training continuous Education and Community Service Centre  |
|  | Dr. Rasmieh Emmar | Faculty member |
|  | Dr. Intesar Tannous | Faculty member  |
|  | Dr. Salameh Aldajah | Faculty member  |
|  | Dr. Wafika Thaher | Faculty member |
|  | Dr. Alaa Abu Alrub  | Faculty member |
| **University of Gabes** |
|  | Dr. Mehdi Khouja | Assistant Professor at Higher Institute of Computer and Multimedia  |
|  | Dr. Mohamed Ouwais Kabaou | Associate professor in Computer Science , Head of E-Learning Department  |
| **University of Sfax** |
|  | Dr. Ismail Bouassida | Associate professor in Computer Science |
|  | Dr. Amine Elleuch  | Associate Professor |
| **University of Sousse** |
|  | Dr. Wassim Jomaa | Associate Professor at Higher Institute of Musicology  |
|  | Dr. Adel Bouallegue | Associate Professor |
| **University of Brescia** |
|  | Dr. Giovanni Mirabella | Associate Professor of physiology |
| **Porto Polytechnic** |
|  | Dr. Carlos Vaz de Carvalho | Associate Professor in the Computer Engineering Department |
| **National and Kapodistrian University of Athens** |
|  | Dr. Sofia Papakonstantinou | Team Member |
|  | Dr Konstantina (Nadia) Tsoli | Assistant Professor at the Department of Primary Education (NKUA) |
| **Universidade Católica Portuguesa** |
|  | Prof. Luís Teixeira | Assistant professor at School of Arts |
|  | Prof. Luis Sá | Assistant professor at Institute of Health Sciences |
| **University of Osijek** |
|  | Dr. Antonija Matic | Head of the Office for EU Projects and Programs  |
| **University College Limburg vzw** |
|  | Ms. Chloë Mentens | Researcher |

# Minutes of the Meeting

The meeting was conducted via zoom video conferencing from 01:00 PM to 03:30 PM Amman Time.

The meeting started by a welcome from the Project Coordinator, Prof. Ahmed Al-Salaymeh.

**Work package leaders** presented the progress in the work packages of HEALING Project (WP2, WP3, WP4, WP5, WP6 and WP7). Also they pointed out what is required from partners as follow:

### WP2: Curricula Development

**Dr. Giovanni Mirabella (UNIBS), Prof. Rami Haddad (UJ) and Dr. Aiman AlShara’ (HU)** discussed “**WP 2. Curricula Development”** with partners and the following were agreed on:

|  |  |  |  |
| --- | --- | --- | --- |
| No. | Task | Responsibility | Due Date |
|  | Arrange a meeting with Dr. Giovanni and Project coordinator with Co leaders to prepare road map for courses preparation. * Collect the expertise of each institution.
* prepare a plan to prepare course outline template with learning outcomes and by (Professional, Vocational, Master, Training Courses …).
* Creation of committees responsible to develop the selected courses.
 | Dr. Giovanni Mirabella (UNIBS), IU, UNIGVB. | Before End of December, 2020 |
|  | Final Study plans (Final Version) should be submitted to Dr. Giovanni. | Eng. Rasha AlBeek | When receiving from JO and TU partners 31.12.2020  |
|  | Art therapy accreditation starting process  | JO, TU | During Jan, 2021 |

### WP3: Capacity Building and Training Workshops (Teacher/Technician Staff & Students)

**Prof. Luís Teixeira** discussed “**WP 3. Development: Capacity Building and Training Workshops (Teacher/Technician Staff & Students)**” with partners. The following were agreed on:

|  |  |  |  |
| --- | --- | --- | --- |
| No. | Task | Responsibility | Due Date |
|  | Prepare a template about training qualifications for each EU partner regarding students and staff and connect it with Healing courses | WP leaders | Before End of December, 2020 |
|  | Prepare a selection criteria for training workshop regarding students and staff. | WP leaders | January, 31st 2021 |
|  | Conduct an online meeting to discuss the capacity plan and its relation to Wp2. | WP leaders and Co-leaders | Between 21.12.2020 – 07.01.2021  |
|  | Preparation for conducting Online training workshops  | WP leaderEU partners  | Jan, 2021 – June, 2021 |

### WP4: Development of the Art Therapy Centre to support the new curriculum

**Dr. Carlos Vaz de Carvalho,** discussed “**WP4: Development of the Art Therapy Centre to support the new curriculum**” with partners, and the following were agreed on:

|  |  |  |  |
| --- | --- | --- | --- |
| No. | Task | Responsibility | Due Date |
|  | Equipment Documents From Tunisian  | TU | Before Jan, 31st 2021  |
|  | Send Art therapy centre template to JO and TU  | IPP and UJ | Before Jan, 7th 2021 |

### WP5: Quality Control and Monitoring (QC&M)

**Dr. Sofia Papakonstantinou,** discussed “**WP5: Quality Control and Monitoring (QC&M)**” with partners, and the following were agreed on:

|  |  |  |  |
| --- | --- | --- | --- |
| No. | Task | Responsibility | Due Date |
|  | Send the evaluation link for 6th meeting to all partners to be filled from Participants | WP leader | One week after the meeting  |
|  | Send the evaluation link from HEALING Website to all partners to be filled  | WP leader | One week after the meeting |
|  | Checking the Google drive  | WP leader  | continuously |

### WP 6: Dissemination & Exploitation

**Dr. Antonija Matic (UNIOS),** discussed “**WP 6: Dissemination & Exploitation**” with partners, and the following were agreed on:

|  |  |  |  |
| --- | --- | --- | --- |
| No. | Task | Responsibility | Due Date |
|  | Conduct dissemination activities (online or physical). | All  | Continuously  |
|  | Send the dissemination collected activities for all partners.  | Eng. Rasha  | 31.12.2020 |
|  | Follow up with 2nd E-Newsletter with responsible institution. | WP leader + Eng. Rasha + Prof. Ahmad Odat | At the end of this year  |
|  | Collect Biannual Dissemination Activities reports from all partners.  | WP leader | End of January, 2021  |

### WP 7: Project Coordination

**Eng. Rasha Al-Beek from UJ,** Summarized the progress of HEALING project.

**Finally, Prof. Ahmed Al-Salaymeh expressed his thankful to all participants in the conducted online meeting and scheduled the seventh SC online meeting to be on Febreuary,2021.**

**(Next meeting date will be chosen by DOODLE)**